## Slide 1
OLA Project
Online Learning Applications — kickoff & plan
Team of 5 · Submission 11 July · Target-ready 23 June
Polimi · M. Castiglioni

## Slide 2
Agenda
01
The project
what we are building and why
02
Tools & platform
Colab, Python stack, repo
03
Team & roles
who owns what
04
Timeline
week-by-week plan to 30 June
05
Ground rules
slides-as-we-go, interface freeze, syncs

## Slide 3
01 · THE PROJECT
Bidding on multiple advertising campaigns
Design online-learning algorithms that choose bids dynamically across N advertising campaigns, under a shared budget B, over T rounds. Each campaign is a first-price auction; winning a slot yields value vᵢ − bᵢ and costs bᵢ.
REQ 1
Single campaign, stochastic
Warm-up. UCB1, then UCB1 with budget constraint.
REQ 2
Multiple campaigns, stochastic
Combinatorial-UCB with budget. Adds the conflict-graph constraint.
REQ 3
Best-of-both-worlds
Primal-dual with budget. Stochastic + adversarial. Full feedback.
REQ 4
Slightly non-stationary
CUCB + sliding window · CUCB + change detector · compare with primal-dual.
Difficulty:
= Easy
= Medium
= Hard

## Slide 4
02 · TOOLS & PLATFORM
What we'll build with
PLATFORM
Jupyter notebook
Free GPUs if we need them, zero setup on teammates' machines.
Easy to show the prof during the presentation — runs in-browser.
One notebook per requirement, imports a shared `ola/` package from the repo.
One notebook per requirement — linked from the main README.
PYTHON STACK
Rolled-by-hand, not a bandit library
We implement the algorithms ourselves — that's what the project is about. Libraries like SMPyBandits or MABWiser would hide the work we need to show.
NumPy
arrays, sampling, stats
SciPy
KL divergence, stats tests, optimization
Matplotlib
all plots — regret curves, detection delay
NetworkX
conflict graph + independent-set enumeration
CVXPY (opt)
primal-dual LP oracle if we go that route
pandas
results CSVs, comparison tables

## Slide 5
03 · TEAM & ROLES
Who owns what
P5
LEAD
Research direction
Coordination + weekly syncs + master deck · OLAM / LNSE literature study · sKL-constellation for non-stationary environment · Theory doc for Req 4 · help P4 throughout
P1
CO-LEAD
Engineering & integration
Repo, CI, base Environment class · Req 1 (UCB1 + UCB1 with budget) · Req 4 final 3-way comparison · float support for P2/P3
P2
Req 2 · Combinatorial-UCB
Multi-campaign joint-distribution environment · Combinatorial-UCB with budget · Experiments + slides inline
P3
Req 3 · Primal-dual
Adversarial / non-stochastic environment · Primal-dual with budget (best-of-both-worlds) · Experiments + slides inline
P4
Req 4 ·
CUCB + sliding window · CUCB + change detector · Theory handed over by P5 · pair-working throughout

## Slide 6
04 · TIMELINE
10-week plan
W1
Apr 21
W2
Apr 28
W3
May 5
W4
May 12
W5
May 19
W6
May 26
W7
Jun 2
W8
Jun 9
W9
Jun 16
W10
Jun 23
Simo
lead
Foad
co-lead
Luigi
Req 2
Mengyao
Req 3
Alessandro
Req 4 (code)
OLAM study + theory doc
Help P3 with env  Constellation distribution idea(?)
Help P4 on Req 4
Repo
Req 1
Float support + Code Review
3-way comparison
Setup
Multi-campaign env
Combinatorial-UCB
Experiments
Setup + study
Adv env
Primal-dual with budget
Experiments
Setup
Read theory doc
CUCB + sliding window
CUCB + change det.
Exp
Jun 9
all algos + drafts
Jun 23
submission-ready
REVIEW & POLISH
Slides are drafted inline — same week the underlying work lands. Review weeks polish; they don't produce first drafts.
Experiments

## Slide 7
04 · TIMELINE
10-week plan
W1
Apr 21
W2
Apr 28
W3
May 5
W4
May 12
W5
May 19
W6
May 26
W7
Jun 2
W8
Jun 9
W9
Jun 16
W10
Jun 23
Simo
lead
Foad
co-lead
Luigi
Req 2
Mengyao
Req 3
Ale
Req 4 (code)
OLAM study + theory doc
Help P3 with env  Constellation distribution idea(?)
Help P4 on Req 4
Repo
Req 1
Float support + Code Review
3-way comparison
Setup
Multi-campaign env
Combinatorial-UCB
Experiments
Setup + study
Adv env
Primal-dual with budget
Experiments
Setup
Read theory doc
CUCB + sliding window
CUCB + change det.
Exp
Jun 15
all algos + drafts
Jun 30
submission-ready
REVIEW & POLISH
Slides are drafted inline — same week the underlying work lands. Review weeks polish; they don't produce first drafts.
Experiments

## Slide 8
04 · TIMELINE
Personal deadlines
#
OWNER
DELIVERABLE
DUE
01
P1
Github config (slides and main files)
Apr 21
02
P1
Repo + CI + base Environment class
Apr 28
03
P5
Design doc · sKL environment + Req 4 theory outline
Apr 28
04
P2
Multi-campaign joint-distribution environment
May 5
05
P5
Theory doc for P4 delivered
May 5
06
P1
Req 1 (both UCB1 variants) + conflict-graph utility
May 12
07
P3
Adversarial / non-stochastic environment
May 12
08
P5
sKL-constellation non-stationary environment delivered to P4
May 19
09
P2
Combinatorial-UCB with budget
Jun 2
10
P3
Primal-dual with budget
Jun 2
11
P4
CUCB + sliding window · CUCB + change detector
Jun 2
12
P1
3-way comparison experiments (on sKL constellation)
Jun 9
13
ALL
All plots generated, all slide drafts in master deck
Jun 9
14
ALL
Dry-run #1 + deck consistency review
Jun 16
15
ALL
Dry-run #2 + Q&A prep + README · submission-ready
Jun 23

## Slide 9
05 · GROUND RULES
How we work together
1
Weekly 15-min sync
Same day every week (Sunday evening ?). Unblockers, demos, decisions written down.
2
Coordination within teams
(P4-P5) and (P2-P3-P5) will work together so can schedule meeting on their own
3
Slides as we go
Each person drafts their 3–4 slides the same week their work lands. No end-of-project crunch.
4
One master slides deck
P5 maintains. Teammates drop slides into their section; consistency pass in W9.
5
Shared results JSON/CSV shared format
Every experiment dumps round · bid · reward · cost · budget_left · cum_regret. Plots are derived. This is fundamental for final result show.
6
Jun 23 target, not Jul 11
18-day buffer for taking times for exams and if something goes wrong

## Slide 10
Let's ship this.
First sync: 28 April. Come with your design-doc draft.
Repo · Colab notebooks · master deck — all linked from the README